## Slide 1
JVA IB Weekly Review
Week 08 — Mar 3–9, 2026
Japan's Venture Academy · Internship Board

## Slide 2
KPI Snapshot
1
This Week's Numbers (W08)
+10
LINE New Students
(Target: 16.7 / week)
+2
Applications
(Target: 8.3 / week)
0
Matches
(Target: 5 / month) ⚠️

## Slide 3
KPI Snapshot
2
KPI vs. Monthly Target (March MTD)
 | Monthly Target | MTD Actual
LINE New Students | 16.7 / week | 12 (72%)
Applications | 8.3 / week | 2 (24%)
Matches | 5 / month | 0 (0%) ❌
Job Cards | 10 / month | ~16 ✅

## Slide 4
Funnel
3
Application Funnel — Cumulative (as of W09)
1
▶
LINE Registration
57 active students
(excl. 7 JBA members)
2
▶
Application
23 total applications
Conversion: 39.0%
39.0%
3
▶
Interview
Pending — no match yet
Blocked at this stage
4
Match
0 matches
Conversion: 0% ← Critical
0%

## Slide 5
Focus
4
This Week's Focus KPI: Match
23 applications have been submitted — the pipeline is filled.
The bottleneck is not awareness or applications. It is the handoff between application and company interview.
Key insight: Most applicants went to Jurin AI (attractive brand), but Jurin AI requires Business Japanese + 35h/week — almost no one qualifies.
High-fit candidates (Jeongmin, Martin) are available now.
0
Matches so far

## Slide 6
Action Plan
5
W08–W09 Action Items
01
Screen & Recommend
Screen Jeongmin & Martin → identify best-fit companies → send recommendations.
Goal: trigger first interview → first Match.
Owner: HR + Sales
Deadline: Mar 14
02
Confirm Job Card
Verify the manually added Job Card entry (company name + contact info) in the KPI sheet.
Goal: unblock company pipeline.
Owner: Sales
Deadline: Mar 13
03
Set Follow-up SLA
Define company follow-up cadence:
• 48h reply SLA
• 5-business-day reminder
Goal: reduce stalled applications.
Owner: PM + Sales
Deadline: Mar 15

## Slide 7
Let's get our first Match this week.
JVA Internship Board — W08 Review