## Slide 1
IB Weekly Meeting
March 12, 2026
Why Is Match Still 0? — Challenges & Next Actions

## Slide 2
1
Where Are We?
59
LINE Registrations (cumulative)
23
Total Applications
0
Matches

## Slide 3
2
Why Is Match Still 0?
Before
• Students apply → Companies respond quickly
• Interviews happen → Match is made
• Funnel flows smoothly
After
• Students apply → Companies go silent
• Few students even reach interview stage
• Students don't meet basic requirements (location, eligibility)

## Slide 4
3
Root Cause #1: Company-Side Bottleneck
Company
Slow or no response
No SLA in place
IBE doesn't follow up
Selection progress invisible

## Slide 5
4
Root Cause #2: Student Condition Mismatch
Based overseas / not in Tokyo
Work eligibility not confirmed
No pre-filter before Apply
No Match

## Slide 6
5
What Do We Change?
 | Option A | Option B
Company response | Set SLA: reply within 5 biz days at onboarding | Weekly push follow-up from IBE to all companies
Student mismatch | Add location + eligibility to application form | Condition check step in LINE before Apply button

## Slide 7
6
Today's Goal
01
Pick 1–2 Actions
Choose what we actually start next week — not a wishlist
02
Assign an Owner
Every action needs one person responsible
03
Set a Deadline
Define when we review the result

## Slide 8
Let's Decide.
IB Weekly — March 12, 2026